## Slide 1: Overview Pilot status and ongoing activities
European Commission SEMIC Group (DG DIGIT) and DG JRC, Publications Office of the European Union
& Member States
Joint Research Centre (JRC)
6th Meeting – June 25, 2025

## Slide 2: Overview 6th Meeting - Meeting objectives
Agenda
https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/tree/main/meetings/2025-06-25

## Slide 3: Overview Past Meeting
Fifth Meeting minutes
Available at:
https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/tree/main/meetings/2025-06-03

## Slide 4: Overview Pilot final report
3rd working draft
Available – Draft based on final contributions from DK, IT, FI, FR and NL.
New contents: Abstract, Conclusions, country-specific updates.
Missing contributions from past meetings included.
Plan
  Final version of the report by 27 June 2025.
    Finish the work in formalising References.
    General quality-checking. Participant-specific revisions.
Issue-resolution: To be organised in mid-July 2025
https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/blob/main/final-report/previous-versions/ISO%26GeoDCAT-AP_Pilot_report_v3.2-20250625.docx

## Slide 5: Overview HVD (geospatial) tagging good practice
Candidate good practice
Available at:
ISO Multilingual
& Non-multilingual
options
https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/tree/main/good-practices/hvd-tagging
https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/blob/main/good-practices/hvd-tagging/ISO_HVD_Tagging_Anchor_Non-Multilingual-clarification.xml
https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/blob/main/good-practices/hvd-tagging/ISO_HVD_Tagging_Anchor_Multilingual-clarification.xml

## Slide 6: Overview HVD (geospatial) tagging good practice
82th INSPIRE MIG-T Meeting
Pilot status, results and conclusions (presentation).
Candidate good practice status
Voting results for potential endorsement by INSPIRE MIG-T.
  19 Member States / countries voted in favour (after conciliation meetings):
    BE, HR, CY, CZ, DE, DK, EE, FI, HU, IE, IS, IT, LU, NL, NO, RO, SE, SK, ES.
ISO Multilingual
& Non-multilingual
options
Potential endorsement at the 82nd INSPIRE MIG-T Meeting