## Sheet1
Origin | Issue | Reported by | INSPIRE Pilot GitHub | SEMIC GeoDCAT-AP GitHub | SEMIC XSLT GitHub | Category | Analisis (for 4th meeting) | Additional notes | ACTION | DONE | 4th Pilot Meeting | 5th Pilot Meeting
Proposed for closure (Pilot repository)
GitHub | Proposal to add hvdCategory as optional to GeoDCAT-AP 3.0 | FI | #3 | Related to #147 | - | (was: GeoDCAT-AP update / Proposal) XSLT extended trasformation proposal | Suggestion in GitHub à 1st review with Jordi NEXT MEETING (this and the similar issue below) @HAGAR answer that only HVD extension requires dcatap:applicableLegislation as Mandatory. | [NEW] After MIF meeting, escalate to SEMIC XSLT space with rule: IF mapping of the tagging results in dcatap:applicableLegislation="http://data.europa.eu/eli/reg_impl/2023/138/oj" THEN the gmd:keyword is to be mapped to dcatap:hvdCategory ELSE it is to be mapped to dcat:theme (??? this we need to discuss. could also be mapped to dct:subject. I think it cannot be mapped to geodcatap:topicCategory becuase this is explicitly used only for INSPIRE theme ("Topic categories in accordance with EN ISO 19115" --> see: https://semiceu.github.io/GeoDCAT-AP/releases/3.0.0/#topic-category-and-keyword-in-datasets-and-dataset-series: "Keywords associated with other controlled vocabularies are mapped to dcat:theme."). see DCAT-AP issue https://github.com/SEMICeu/DCAT-AP/issues/316 (OPEN) asking how to encode additional themes | Contine discussion in #147. also to be considered for data services | DONE | NEXT MEETING - @HAGAR / @LENA | agreed that 1st step can be limited to resources that explicitly refer to HVD ELI.
GitHub | Transformation: HVD Category | ES | #7 | - | - | XSLT Transformation issue | In progress. Awaiting update of XSLT to transform HVD attributes. @JORDI | [JORDI]: This is known. SEMIC is waiting for the endorsement of the HVD tagging good practice candidate to update the XSLT accordingly. | JORDI - See: https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/issues/7#issuecomment-2786579856 | DONE | MOVE TO SEMIC asking to update the XSLT transformation once the HVD tagging GP is endorsed. | discussed
GitHub | Transformation: namespaces and standards | FI | #5 | - | - | XSLT Transformation update / Clarification requested | Suggest to move to GeoDCAT repo. @SEMIC | [HAGAR]: If endorsed, ensure both ="http://data.europa.eu/930/" and "http://data.europa.eu/r5r/“ are included as NSs in the XSLT transformations | JORDI - See: https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/issues/5#issuecomment-2786611280 | DONE | MOVE TO SEMIC
GitHub | Proposals related to the HVD tagging good practise and the XSL transformation | FI | #2 | Related to #134 | - | HVD Tagging Good Practice / Vocabularies / XSLT Transformation update / Proposal | @HAGAR comment in GitHub (pt. 1); @SEMIC for pt. 2 (XSLT transformation update) | [HAGAR]: 1. could the the ELI-codes of High Value Dataset/ODD legislation and the INSPIRE Directive be added to the list of this metadata code list https://inspire.ec.europa.eu/metadata-codelist/PriorityDataset  IMO no because the expectation is to refer directly to the legislation (range is https://semiceu.github.io/DCAT-AP/releases/2.2.0-hvd/#LegalResource) so a skos:Concept is not compliant. 2. wrong mapping  awaiting updated XSLT for HVDs | HAGAR 1st suggestion -> see: https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/issues/2#issuecomment-2799894982 FOR the 2nd point - this is for SEMIC for when the Pilot is concluded [NEW]: continue discussion in: (https://github.com/INSPIRE-MIF/helpdesk-registry/issues/115 | DONE & SEMIC | NEXT MEETING - @OP/Conterra | discussed
2nd Meeting | Mapping from INSPIRE themes to HVD category may create false positives of HVDs on national portals | DK (1) |  |  |  | General issue | It should not be an issue any more if the HVD tagging good practice is used. TBV the current reporting looks for HVD theme+applicable legislation. |  | Resolved | DONE
Open issues - Previously discussed - SEMIC GeoDCAT
GitHub | Add 'HVD category' and 'documentation' properties related to high-value datasets | IT | Related to #3 | #147 | - | GeoDCAT-AP update / Proposal | @HAGAR (analyse and post) | (Pilot tag missing) [HAGAR]: Also see: Proposal to add hvdCategory as optional to GeoDCAT-AP 3.0 above (https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/issues/3). Suggestion to add dcatap:HVDCategory to GeoDCAT-AP (would have to be O.). Need to consider semantically that the OP Tax states: “It is not recommended to use these data categories outside the context of legislation on the re-use of public sector information.” So IF only HVD (Geo) datasets have the HVDcategory than I would be against adding it to GeoDCAT |  | DONE | See #3 | see pilot #3
GitHub | conflicting namespace prefix in geodcat-ap-SHACL.ttl | NL | - | #145 | - | GeoDCAT-AP validation / SHACL | SHACL wrong NS prefix @SEMIC | [HAGAR]: the xslt is declaring dct: (shacl “dc:”) | @SEMIC. | DONE | ON SEMIC
GitHub | A.7.13 Spatial resolution - text and provided example are confusing | NL | - | #144 | - | GeoDCAT-AP update / Clarification requested | Text and example in GeoDCAT-AP v.3 not clear. Ask for the user to propose an alternative text. @SEMIC |  | JORDI - See: https://github.com/SEMICeu/GeoDCAT-AP/issues/144#issuecomment-2786627846 | DONE | ON SEMIC
GitHub | guidance on the use of prov:qualifiedAttribution on Dataset would be welcome | NL | - | #143 | - | GeoDCAT-AP update / Clarification requested | IMO the explanation in GeoDCAT is clear @SEMIC | [JORDI]: I would request the user to further explain what is not clear, or better to provide the proposed updated to GeoDCAT-AP 3, before coming back to SEMIC on this issue. [HAGAR]: 11. Agent roles : “As such, [the PROV attribution] MAY be used in combination with or to complement the [GeoDCAT-AP] property-based approach, but it MUST NOT replace it. For instance, it can be used to specify roles not covered by the agent role properties used in GeoDCAT-AP, and/or to specify additional information that cannot be expressed via a property (as the period during which an Agent covered a given role).” See also A.7.16 (https://semiceu.github.io/GeoDCAT-AP/releases/3.0.0/#responsible-party-and-metadata-point-of-contact---dataset-responsible-party-and-metadata-point-of-contact) and Example 40 (https://semiceu.github.io/GeoDCAT-AP/releases/3.0.0/#ex-mapping-responsible-party) and example 12 (https://semiceu.github.io/GeoDCAT-AP/releases/3.0.0/#ex-attribution) | @SEMIC. | DONE | NEXT MEETING - @HAGAR | Resolution agreed
GitHub | create the geodcat-ap shacl file as an extension to the dcat-ap shacl file | NL | - | #142 | - | GeoDCAT-AP validation / SHACL | This is about the need or not to include dcat-ap shapes in the godcat-ap shapes. @SEMIC | [HAGAR]: See also https://github.com/SEMICeu/DCAT-AP/issues/399. | @SEMIC | DONE | ON SEMIC
GitHub | misalignment between GeoDCAT-AP dct:Standard properties and XSLT transformation rules | NL | - | #141 | - | XSLT Transformation update / GeoDCAT-AP validation / SHACL | XSLT transformation omits typing as skos:Concept for referenceSystem and serviceProtocol (and probably some more). @SEMIC | [HAGAR]: If SEMIC creates distinct Shapes may not have to resolve… otherwise XSLT should be updated. | @SEMIC | DONE | ON SEMIC
Related to #111
3rd Meeting | Align vocabulary for the accessRights property | IT | - | #150 | - | Vocabularies | Contact IT for asking to publish the issue in GitHub |  | @Jordi - IT contacted |  | PENDING TO EVALUATE | @Hagar to suggest a mapping of terms from INSPIRE list to OP ones based on the discussion
Open issues - Previously discussed - SEMIC iso-19139-to-dcat-ap
GitHub | Improve mapping to dcat:Distribution | SEMIC also FR | - | - | #57 | XSLT Transformation update / GeoDCAT-AP update / Proposal | @SEMIC |  | @JRC - follow up in 2nd pilot (topic: mapping of CI_OnlineResource to DCAT) | DONE | ON SEMIC
2nd Meeting GitHub | gmd:purpose -> how to map? (suggested also to dct:description) | DK (2) | - | - | #70 | GeoDCAT-AP mapping | @HAGAR to check and if accepted add to XSLT in description (no other properties identified) OR geodcatap ext??? | Similar issue reported by ES in 3rd meeting | @SEMIC - move to GeoDCAT repo (specifiction update: new property) | DONE | NEXT MEETING - @HAGAR | Ageement reached to add a new geodcat:purpose property
3rd Meeting GitHub | XSLT - transformation failed because of the bilianguality of the gmd:country item | CZ | #11 | - | #73 | XSLT Transformation issue | Issue when ISO uses bilingual country name. ES reports similar issue. Review XSLT. FI mentions similar issues with extended profile @SEMIC |  |  | DONE | ON SEMIC
|  | ES |  |  | #52
3rd Meeting GitHub | More than one dataset indentifier | CZ | - | - | #71 | XSLT Transformation issue | Potential issue when using multiple IDs in ISO. @SEMIC |  |  | DONE | ON SEMIC
3rd Meeting GitHub | Duplicity of schema:startDate/schema:endDate after transformation | CZ | - | - | #72 | XSLT Transformation issue | XSLT now adds dcat:start/endDate while maintaining th schema:start/endDate. SEMIC requested feedback for the suggest to remove the schema mapping @SEMIC | @Hagar - explain the issue in meeting and request feedback (Jakub: "We could remove the DCAT1 version, if there is consensus.") -> this would mean that support for DCAT V.1 is removed | awaiting feedback | DONE | ON SEMIC
3rd Meeting | 1 bounding box in ISO XML, 4 instances of locn:geometry and 4 instances of dcat:bbox | IT | - | #68 | #76 | XSLT Transformation issue | Contact IT for asking to publish the issue in GitHub | To be added as GitHub issue. Also related to SEMICeu/DCAT-AP#265 and SEMICeu/DCAT-AP#175 | Either lift the cardinaly of serialisations (similarly to how dct:title with multilingual values is treated) OR agree on a single serialisation |  | PENDING TO EVALUATE | If only one serialisation is to be used, participants expressed no preference (should by GML or WKT)
|  | NL |  |  | #64
3rd Meeting | Only WFS and WMS services are considered in the transformation as Distribution. A direct URL for downloading the dataset is not considered | IT |  |  | #74 | XSLT Transformation issue | @SEMIC |  |  | DONE | ON SEMIC
Open issues - Pilot
All Meetings | Many MSs work with (Geo)DCAT v.2 | Country reports | - | - | - | General issue | Main class added in v.3 is DatasetSeries (in ISO recognisable when hierarchyLevel = ‘series’) | Verify with SEMIC that XSLT can be used with any DCAT version transforming all HVD attributes (e.g. applicableLegislation and HVDclassification). Only issue may be then that Series will not be shown correctly. | Highlight it in the final report.
- | Need to check which ISO fields have been left out from the XSLT transformation. | Jordi | - | - | - | XSLT Transformation completeness / Extended mapping | Need to check if other fields apart from those raised by Spain are left out. @JORDI to list of ISO fields to see what’s left out. @HAGAR to check which ISO attributes that are transformed in the XSLT |  | @JRC - follow up in 2nd pilot (topic: information loss in mapping)
GitHub | Transformation: The same key words emerge twice | FI | #6 | - | - | XSLT Transformation issue | Local issue . Perhaps see if we can replicate with chosen INSPIRE compliant record. Ask if any other participants have the same issue. @JORDI | [HAGAR]: ISO: https://paikkatietohakemisto.fi/geonetwork/srv/api/records/78750e14-35bd-4e54-b1af-e49a079d81f4/formatters/xml?approved=true DEU: https://data.europa.eu/data/datasets/78750e14-35bd-4e54-b1af-e49a079d81f4?locale=en (no keywords included) @See with OP. this looks like a bug in their harvesting | JORDI - See: https://github.com/INSPIRE-MIF/GeoDCAT-AP-pilot/issues/6#issuecomment-2786597270 | DONE | Wait until reproduced.
GitHub | Role of service metadata in the EDP, in HVD-reporting and in this pilot? | FI | #4 | - | - | (was: European Data Portal / Clarification requested) encoding and transforming service metadata | @OP | [HAGAR]: Data service are included in OP MD. We may want to verify if they are reported correctly in the Reporting app (https://data.europa.eu/apps/hvd-reporting-tool/reports.html). Note that it is possible to restrict search to include data services in DEU: | Issue #4 can be closed. @JRC - follow up in 2nd pilot (topic: provision and transformation of service metadata) | DONE | NEXT MEETING - @OP/Conterra | Continue discussion
2nd Meeting | All formats (gmd:distributionFormat) is listed in each dcat:Distribution | DK (2) | #8 | - | - | XSLT Transformation issue | XSLT (19139) transformation done with https://github.com/Saxonica/Saxon-HE/releases/tag/SaxonHE12-5 | Issue created | @JRC - follow up in 2nd pilot (topic: mapping of CI_OnlineResource to DCAT)
related to #10
3rd Meeting | Useful to have a common place to share national XSLTs for local uses | FR | - | - | - | General issue / Proposal | Propose to discuss in the next meeting. | [HAGAR]: Propose to use pilot repository? | @Jordi (include reference to location in final report?) | DONE | NEXT MEETING - @JORDI
5th meeting | Transformation: Distribution, LandingPage and Documentation | FI | #9 | - | #57 | XSLT Transformation issue | The issue is part of the larger discussion on the need for improved transformation of Services and Distributions |  | @JRC - follow up in 2nd pilot (topic: mapping of CI_OnlineResource to DCAT) |  | -